## Sheet1
Item Number | Status | Type of Issue | Priority | Defect/Enhancement | Description
Please add images to image tab and reference
3 | Open | Function | High | Defect | Rename App "CrisisCalm" and use Logo in design
6 | Open |  | Medium | Defect | Missing Load Screen and App Icon - "Crisis Calm"
10 | Open | UI |  | Defect | Image 1.4 - the four choices (I'm worried, I'm scared, I'm caught up, Something else") should fit on the one page with no need to scroll up / down
13 | Open | UI |  | Defect | Image 1.5 - In the first sequence replace "Now I'll help you relex" with "I'll help you to calm down"
14 | Open | UI |  | Defect | Image 1.5 (and all pages in sequence) - In monkey speech bubble correct language "Whick option looks like more attractive" to "Which option looks more attractive?"
15 | Open | UI |  | Defect | Image 1.6 (and all similar sorting pages) - the four choices should fit on the one page (remove narrow scroll)
19 | Open | Function |  | Enhancement | Image 1.8 - this image is at the end of the second sequence ie "help you relax" . At this point and for all of the selection and sorting pages from this point forward (ie S3a to S4h) we want the user to be able to at any point be able to leap forward to the guage (S.5.1) rather than being locked into cycling through all of S3a to S4d before they get to it. If you look at the original design at S2h it is taken at the same point as Image 1.8. In S2h we had a "head" icon appear at the bottom and then you will see this icon remains in place all the way through the remaining steps. Double tapping this icon sends the user to the guage (S5.1) and allows them to finish the process from there. Note: in the original design the icon stayed in place through S5.1 to S6c_1 but in reality it should not be active from S5.1 onwards or it will create an unecessary loop back to the guage. So what we are doing is forcing the user to do a minimum of two sequencies (ie. help you calm down / help you relax) and then allowing them to skip all or part of the third and forth sequences (ie help you see what is ok in the present / show you how alright things really are) by using the icon to jump forward to the guage.
21 | Open | Function |  | Enhancement | Image 1.9 - If you refer to the original S5.1 you will see a curved "replay" arrow icon in the bottom left hand corner. This replay icon is there to allow the user to go back immediately to another sequence in case they realise that they need to keep going. In simple terms tapping the icon takes the user back to the first sequence "help you calm down" and then the user can run through the whole process all again (with different randomised sentences to choose from of course not the same as the last time they did it). This replay icon should stay in place for the whole of the guage section and then come off at S5a / S5b.
26 | Open | UI |  | Defect | Image 1.12 - (this is the first page after selecting "SOMETHING ELSE") - In the Prevention box the last sentence should read "prevent something from happening". The last box should be "SHOW ME THE FULL LIST". Ideally the 5 text boxes here should fit on the one page so that there is no need to scroll up or down
30 | Open | Function |  | Enhancement | we need to rethink how this calibration works. In the original mock up the calibration was not fully developed and I realise now it needs some explanation/re-work. The purpose of calibration is to present the user with the full list of 36 reactions from the "Full Reaction List" and then have them work their way down to a selection of just 3 which then become the basis for the initial launch questions. The problem is that asking someone to select 3 from 36 choices is actually really difficult so we need a way to step the choice down into manageable decisions. When the user gets to Image 1.15, they should be able to pick any number (so 1 to 36 choices) of reactions (so the user could pick 36 for example). If they pick just 1, 2 or 3 reactions in Image 1.15 and then press the arrow then we actually have the info we need and they can advance forward to what was the original Cal-5 (meaning if they only have one choice that we present that at launch and then randomise the other 3 etc). If they select 4 or more reactions and then press the arrow, then the monkey represents those selected reactions (only) and has to work through a stepped decision path in order to get them to refine the selection down to 3. The logic for this decision could be: (A) if the user has selected between 4 and 9 reactions, the monkey then asks them to select 3 from that new refined list. (B) If the user has selected between 10 and 20 reactions, we ask them to refine that choice to "no more than 9", then the monkey represents those (up to) 9 selections and asks them to pick 3. (C) If the user has (which is unlikely but possible) selected more than 20 reactions, then we represent the list and ask them to select "no more than 18", then we represent that list and (i) if the number is more than 9 ask them to refine it down to 9, and then represent that 9 and refine down to 3. (ii) if the number is less than 9, we represent the list and ask them to pick 3. Hopefully this makes some sense but if not lets discuss.
31 | Open | UI |  | Defect | Back Buttons doesn't back - it just takes to start (e.g. Halfway through calibration it doesn't go back)
32
16 | Open | Function |  | Enhancement | The sorting function (ie put the four sentences in order) doesn't presently operate as envisaged. If the order has by chance come out with the "easiest" sentence right at the top it is frustrating because you have to try and move the top one out and then back into position before the app will advance. There is also nothing to indicate that you have locked each choice into place. Changes: (1) In each of right hand boxes, in place of the "=" there should be a top to bottom number sequence - 1, 2, 3, 4 - so it is clear when a sentence is moved from fourth position to first (for example). (2) To address the issue of someone wanting to keep the order (wholly or partially) as presented we will need to consider either: (A) having an empty slot that represents the choice to be made (1st, 2nd, 3rd) that is positioned above the four sentences to begin with, and then when the 1st choice is made and dropped into the empty slot, the slot then reappears below that sentence (but above the remaining three sentences) ready for the 2nd choice to be moved in...then down again for the third. Once the third choice is made the user can reorder them with drag and drop (B) alternatively we need to have a cleaner way for the user to double tap a sentence to keep it locked in place (with maybe a slight colour change to the sentence to show it is selected). Happy to discuss further.
33 | Open | Function |  | Defect | require small pause between each "speach". at the moment the monkey says everything (all lines of text) all at once, rather he needs small steps each
7 | Closed | UI |  | Defect | Text below Monkey on entry page should read "Let's calm down"
8 | Closed | UI |  | Defect | Image 1.3 - if you scroll down there are 3 or 4 "Something else" boxes but there should be just one "SOMETHING ELSE".
9 | Closed | UI |  | Defect | Image 1.4 (and this happens on all pages) - chat box is misaligned. The monkey's head is a little too low and the space for text is too compressed by a static dark blue block "header". The blue block should be able fill with the text bubbles as they scroll up in the 'conversation'. In my version I can only see a couple of lines each time and on every page.
11 | Closed | UI |  | Defect | Image 1.4 - correct spelling and change lowercase "something else" to uppercase "SOMETHING ELSE"
12 | Closed | UI |  | Defect | Image 1.4 - The text in "I'M SCARED and "I'M CAUGHT UP" has been cut off so the sentences are not complete
1 | Closed | UI | Medium | Defect | Monkey Icon in Chat is pixelated
2 | Closed | UI | High | Defect | Grey Box appears during calibration on last page of validation
4 | Closed | UI | Medium | Defect | Image 1.1 chat-text misaligned
5 | Closed | UI | Medium | Defect | Image 1.2 Chat-text misaligned + first bubble greyed out first line (chat should appear 1... wait... 2..)
16 | Closed | Function |  | Enhancement | Image 1.6 - the sorting function doesn't presently operate as envisaged. If the order has by chance come out with the "easiest" sentence right at the top it is frustrating because you have to try and move the top one out and then back into position before the app will advance. There is also nothing to indicate that you have locked each choice into place. Changes: (1) In each of right hand boxes, in place of the "=" there should be a top to bottom number sequence - 1, 2, 3, 4 - so it is clear when a sentence is moved from fourth position to first (for example). (2) To address the issue of someone wanting to keep the order (wholly or partially) as presented we will need to consider either: (A) having an empty slot that represents the choice to be made (1st, 2nd, 3rd) that is positioned above the four sentences to begin with, and then when the 1st choice is made and dropped into the empty slot, the slot then reappears below that sentence (but above the remaining three sentences) ready for the 2nd choice to be moved in...then down again for the third. Once the third choice is made the user can reorder them with drag and drop (B) alternatively we need to have a cleaner way for the user to double tap a sentence to keep it locked in place (with maybe a slight colour change to the sentence to show it is selected). Happy to discuss further.
17 | Closed | UI |  | Defect | Image 1.6 - monkey speech bubbles need to be realigned - this seems to be an issue throughout as all bubbles should be left aligned
18 | Closed | UI |  | Defect | Image 1.7 - fix spelling of "releax" to "relax" in monkey speech bubble.
28 | Closed | UI |  | Defect | Image 1.14 - (this is the calibration section). The sentences are cut off under the headings "I'm in dispair" (as shown in 1.14) and also in "I'm Demotivated", and "I'm creating my fear". Also, the header "I'm worrying about my" is cut off and should read "I'm worrying about my behaviour". Note: the header "I'm worrying about my behaviour" seems to cause issues in a couple places because it is has too many words - maybe just change it to "Worrying Behaviour" everywhere.
20 | Closed | UI |  | Defect | Image 1.9 - correct spelling of "further"
22 | Closed | UI |  | Defect | Image 1.10 - check alignment of text
23 | Closed | Function |  | Defect | Image 1.10 - when the user selects "More" at this point the app should default back to the beginning of the "How do you feel right now" sequence (Reaction-1 in the original). In the current version the app defaults to the launch page which is not correct.
24 | Closed | Function |  | Defect | Image 1.11 - when the user selects "Still not great" at this point the app should default back to the beginning of the "How do you feel right now" sequence (Reaction-1 in the original). In the current version the app defaults to the launch page which is not correct.
25 | Closed | UI |  | Defect | Image 1.11 - correct the spelling of "relaxed"
27 | Closed | UI |  | Defect | Image 1.13 - (this is the page after selecting "Show me the full list") There is an error in the logic here because the app is not picking up the correct list. What should be picked up here is the "Full Reaction List" in the original excel spreadsheet. The App is partially picking up the list but not matching the correct headers or cutting them short. For example, in Image 1.143 there are two "I'm Worrying" headers. The first one is line 28 from the Full Reaction List and it should be "I'm worrying about things". The second "I'm worrying" is line 29 and should be "I'm worrying about my behaviour". There should be no duplication of headers at all in this section. If the issue is something to do with the amount of available space we could consider adopting the list style from the calibration section and instead of advancing by selecting the arrow the person could just tap the sentence to select it.
29 | Closed | Logic |  | Defect | Image 1.15 - (this is the calibration section). THIS COULD BE CONFUSING SO MIGHT BE EASIER TO TALK THROUGH In Image 1.15 I had only selected two viewpoints and then monkey speech bubble came up telling me I needed to select my favourite "three". I couldn't advance until I selected a third. Then if you go to image 1.16, I have selected 4 sentences (can't select any more than that) but because I haven't only got three I can't go forwards but I also can't go back to unselect one to reduce it to three - so I'm stuck. This issue aside we need to rethink how this calibration works. In the original mock up the calibration was not fully developed and I realise now it needs some explanation/re-work. The purpose of calibration is to present the user with the full list of 36 reactions from the "Full Reaction List" and then have them work their way down to a selection of just 3 which then become the basis for the initial launch questions. The problem is that asking someone to select 3 from 36 choices is actually really difficult so we need a way to step the choice down into manageable decisions. When the user gets to Image 1.15, they should be able to pick any number (so 1 to 36 choices) of reactions (so the user could pick 36 for example). If they pick just 1, 2 or 3 reactions in Image 1.15 and then press the arrow then we actually have the info we need and they can advance forward to what was the original Cal-5 (meaning if they only have one choice that we present that at launch and then randomise the other 3 etc). If they select 4 or more reactions and then press the arrow, then the monkey represents those selected reactions (only) and has to work through a stepped decision path in order to get them to refine the selection down to 3. The logic for this decision could be: (A) if the user has selected between 4 and 9 reactions, the monkey then asks them to select 3 from that new refined list. (B) If the user has selected between 10 and 20 reactions, we ask them to refine that choice to "no more than 9", then the monkey represents those (up to) 9 selections and asks them to pick 3. (C) If the user has (which is unlikely but possible) selected more than 20 reactions, then we represent the list and ask them to select "no more than 18", then we represent that list and (i) if the number is more than 9 ask them to refine it down to 9, and then represent that 9 and refine down to 3. (ii) if the number is less than 9, we represent the list and ask them to pick 3. Hopefully this makes some sense but if not lets discuss.

## Images
Image 1.1
image 1.2
Image 1.3
Image 1.4
Image 1.5
Image 1.6
Image 1.7
Image 1.8
Image 1.9
Image 1.10
Image 1.11
Image 1.12
Image 1.13
Image 1.14
Image 1.15
Image 1.16